## partners-in-scrime
Partners in Scrime
The best team there ever was, working on Minesweeper together
Milestone 4 - Final Game Board Module Sprint 1
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Refactor Game Board pages | Use AJAX Forms (to avoid page refreshes), Use Partial Pages (to avoid page refreshes), Use Partial Views (to promote reuse and modularity) | Max Weber, Kayla Currier |  | 2021-03-07 | 3 | v
Subitems | Name | Responsible | Status | Date
| Use AJAX Forms (to avoid page refreshes) | Max Weber
| Use Partial Pages (to avoid page refreshes) | Kayla Currier
| Use Partial Views (to promote reuse and modularity) | Max Weber, Kayla Currier
Fully functioning Minesweeer Game Board |  | Max Weber, Kayla Currier |  | 2021-03-07 | 2 | v
Encapsulate all Game Logic & Rules in backend business service |  | Max Weber |  | 2021-03-07 | 2
Daily Sync to GitHub |  | Max Weber, Kayla Currier |  | 2021-03-07 | 0 | v
|  |  |  | 2021-03-07 | 7 | 3/4
Milestone 4 - Final Game Board Module Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Fully Functioning Login & Registration Pages |  | Kayla Currier |  | 2021-03-07 | 2 | v
Refactor code as identified during peer code reviews & instructor recommendations | OR place refactor work as future scrum task in Scrum Back Log | Max Weber, Kayla Currier |  | 2021-03-07 | 2
Subitems | Name | Responsible | Status | Date
OR place refactor work as future scrum task in Scrum Back Log
Update Sprint Stuff |  | Max Weber, Kayla Currier |  | 2021-03-07 | 0.5 | v
Design Report | ER Diagram, Class Diagrams, Flow Charts | Max Weber, Kayla Currier |  | 2021-03-07 | 0.5 | v
Subitems | Name | Responsible | Status | Date
ER Diagram
Class Diagrams
Flow Charts
Retrospective |  | Max Weber, Kayla Currier |  | 2021-03-07 | 0.5 | v
Daily Sync to GitHub |  | Max Weber, Kayla Currier |  | 2021-03-07
|  |  |  | 2021-03-07 | 5.5 | 4/6
Milestone 5 - Save/Restore Game Progress & REST API Sprint 1
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Save Game State |  | Max Weber, Kayla Currier |  | 2021-03-28 | 4 | v
Save Game Results | Number of Clicks, Time spent | Max Weber |  | 2021-03-28 | 2 | v
Subitems | Name | Responsible | Status | Date
Number of Clicks
Time spent
Publish Game Results in REST Service |  | Max Weber, Kayla Currier |  | 2021-03-28 | 4 | v
Daily GitHub Sync |  | Max Weber, Kayla Currier |  | 2021-03-28 |  | v
|  |  |  | 2021-03-28 | 10 | 4/4
Milestone 5 - Save/Restore Game Progress & REST API Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Code Cleanup |  | Max Weber, Kayla Currier |  | 2021-03-28 | 3
Update Sprint stuff |  | Max Weber, Kayla Currier |  | 2021-03-28 | 0.5 | v
Retrospective |  | Max Weber, Kayla Currier |  | 2021-03-28 | 0.5 | v
Design Report |  | Max Weber, Kayla Currier |  | 2021-03-28 | 0.5 | v
Daily GitHub Sync |  | Max Weber, Kayla Currier |  | 2021-03-28
|  |  |  | 2021-03-28 | 4.5 | 3/5
Milestone 6 - Final Project/Presentation: Completed Game Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
IoC dependency injection |  | Max Weber, Kayla Currier |  | 2021-04-18 | 3
HTTP Request filter(page security?) |  | Max Weber, Kayla Currier |  | 2021-04-18 | 3
|  |  |  | 2021-04-18 | 6 | 0/2
Milestone 6 - Final Project/Presentation: Completed Game Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Code Cleanup |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1
Final Retrospective |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
Project Presentation |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
Final Sprint Stuff |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
Final Design Report |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
|  |  |  | 2021-04-18 | 5 | 4/5
Notes
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
C O L O R S C H E M E
[5 empty] | 0 | 0/1